## Sheet1
# | Risk Description | Date Identified | Cause | Severity | Likelihood | Category | Impact | Date to Resolve | Owner | Mitigation | Response
|  |  |  | Low | Low | Technical | Schedule |  |  | Avoidance
|  |  |  | Medium | Medium | Project Mgmt | Budget |  |  | Transference
|  |  |  | High | High | Market | Scope |  |  | Mitigation
[6 empty] | External | Schedule / Scope |  |  | Acceptance
[6 empty] | Organizational | Schedule / Budget
1 | Storage controller final firmware not ready at DVT stage | 2012-02-10 | Bugs detected at beta release were too severe to address in time originally allocated for final release. | High | Medium | Technical | Schedule / Budget | 2012-02-24 | SW / FW Engr | Acceptance | Add additional human resource to FW development team
2 | NAND flash memory not available from manufacturer for PVT build at ODM | 2012-02-10 | NAND MP delivery lead time from vendor longer than originally provided | Medium | Medium | Technical | Schedule / Budget | 2012-02-17 | Procurement | Mitigation | Turn to NAND spot market rather than direct, which means we may need to pay 5% premium
3 | PCB requires 3rd spin to correct "stand-by power too high" issue | 2012-02-10 | EVT2 testing revealed design flaw not captured at EVT1 | High | Medium | Technical | Schedule | 2012-02-12 | Prod Dev Engr | Acceptance | Start EVT3 PCB layout as soon as possible
4 | ID feedback and selection delayed beyond 1-week baseline | 2012-02-10 | Stakeholder responsible for deliverig feedback and acceptance was sick | Medium | High | External | Schedule | 2012-02-17 | Mktg Prod Mngr | Acceptance | No response; need to wait until responsible stakeholder is back in the office
5 | Housing supplier tooling lead time too long based on RFQ response | 2012-02-10 | Tool design too challenging for 2 suppliers | Medium | Medium | Technical | Schedule / Budget | 2012-02-24 | Procurement | Mitigation | Qualify (add to AVL and perform factory audit) supplier no.3
6 | Flash drive performance inadequate with xxx NAND | 2012-02-10 | NAND only supports 2-channel operation | Medium | Medium | Technical | Schedule / Scope | 2012-02-17 | Prod Dev Engr | Avoidance | Do not use xxx NAND; qualify yyy NAND for this product
7 | PVT test failure rate at ODM above 2% | 2012-04-02 | NAND errors at production test | High | Low | Technical | Schedule / Budget | 2012-04-05 | Prod Engr / QE | Mitigation | Introduce NAND screening at 3rd party test house; it will affect MP start schedule
8 | Packaging design release delayed | 2012-02-10 | Mktg Prod Mgr didn't submit several deliverables on time due to unexpected business trip | Low | Medium | Organizational | Schedule | 2012-02-12 | Pack Engr | Acceptance | No response; need to wait until responsible stakeholder is back in the office
9 | Not adequate work effort planned for SW development | 2012-01-14 | SW functionality scope changed after planning phase | High | Medium | Project Mgmt | Schedule / Budget | 2012-01-28 | Prj Mngr | Mitigation | Revise schedule to account for additional 3wk task duration
10` | Product no longer competitive in the market place due to price or performance | 2012-03-16 | Price-to-performance factor no longer attractive from end-user point of view | High | Low | Market | Scope | 2012-03-23 | Mktg Prod Mngr | Avoidance | Explore using higher performance storage controller - increased performance will justify higher price